## Slide 1: Project 5
Barbora Orackova

## Slide 2: Initial Idea
For my final project, I am going to create a performance to raise money for charity. I want to raise money for children with cancer, in order to do this, I will search for charities that will sponsor me. I will also collaborate with Michael, Jack, James P, and James H with this band I will perform covers but also a song of my own where I will write a song with two languages combined Slovak and English. I also asked my mom to help me with this project so we decided to sing some of the Slovakian folk songs to show some of my cultures and how different is Slovakian folk compared to others. I might also need backing vocalist for one or two songs so for this I decided to borrow a choir for this. However if they won’t be able to attend this I will look for backing vocalists.

## Slide 3: Aims and Objectives
Aims :
I want to create a performance to raise money for children with cancer. I also want to show a tiny bit of my culture by singing Slovak folk songs. However, I'm also going to write my own song in both of the languages combined.
Objectives:
I’m going to search for a charity
Research about folk music and songwriting
Set up a band
Rehearse
Create a timetable for practice and for our improvements
Invite people and create posters
Perform

## Slide 4: Target Audience
People who like Slovak folk songs or English pop songs. People who are bilingual. Also, people that donate money to different charities.
Young people that are interested in pop songs. Also family and friends and people that might be interested in folk songs.

## Slide 5: Research
history of Slovakian folk music (theory)
song choices
Songwriters (pop music/Slovakian folk music)
Books
Internet
Family

## Slide 6: Health and safety
Trip hazards- make sure the cables are in the right place, so no one can trip over them
Electrocution Hazard- make sure there isn’t any water or any type of drink near the cables and also that the cables aren’t damaged
Fire Hazard- making sure fire exits are safe and clear
Noise Hazards- make sure the instruments aren’t too loud and people siting closer to the band will wear earplugs
Crushing – find a venue suitable to the number of audience so they won’t be squashed there
Lifting – not lifting something correctly can cause an injury
During a live sound performance there can be many accidents especially when setting up, for this not to happen we need to be careful how we set everything out and maybe ask one of the tutors to check everything before we perform so there aren’t any technical issues.

## Slide 7: Things that could go wrong
Someone could get ill so we would have to rehearse without the band member or even worse someone could get ill at the day of the performance
We can’t get a venue
There wouldn’t be much of an audience
We can have problems with the instruments
We won’t be prepared
We might forget our parts

## Slide 8: How will we fix them
we will have to be able to perform without a particular instrument
If we won’t be able to get a venue then we would have to perform in college
To attract the audience I will have to create posters for the event and put them in different buildings
Before the performance we will need to check all the instruments and if everything is working
We need to rehearse as much as we can but also rehearse individually

## Slide 9: Budgets and finances
All the money we will get from the gig will be donated to a charity for young adults with cancer. However first we need to figure out how we will earn some money and how this will attract the audience. To do this I will have to find a charity that we will perform for, this might also increase the number of an audience because they can support us by giving out posters. This will help us earn more money.

## Slide 10: Timetable
Research (theory) talk about the project, setlist and band name
Research, rehearsal and evaluate on our strengths and weaknesses
Rehearse, continue improving an original song ,contact a certain charity and find a venue
Rehearse , talk about improvements
Rehearse,figure out in what order we are doing the songs
Rehearse , make sure everything is organized
Final Performance
Evaluation

## Slide 11: Evaluation
For my evaluation I will probably write everything up on digital space because it will take less time but also I can work at home and add my improvements but also create myself a target.
However, while we will be rehearsing I will need to make sure I write every single problem we have and how we deal with. This will show us how successful we became throughout time but also we will know what to do next and what we need o improve at the most.
To make sure I will finish my evaluation I will need to know how successful we were and by this I might ask the audience how they liked our performance but also ask my tutors if there could be any improvements.